PROPFLO

Microsoft-Stack Build Proposal

Bridging-Finance Platform — Blazor · Umbraco CMS · .NET MAUI · Power Platform · Azure · Claude AI

Three delivery phases · Claude document extraction with human review · no per-agent licence fees

Prepared for:  PropFlo / Newco

Blended rate:  R850 per hour (excl. VAT)

Date:  4 July 2026

Why a pure Microsoft stack. One vendor, one identity, one support surface. The code that matters — the Blazor admin, the .NET API, the MAUI mobile app and the Umbraco site — is owned by PropFlo outright; the workflow runs on the licensed Power Platform. Agents use PropFlo’s own apps, so there are no per-agent platform fees at any volume — the cost that made the Retool route risky is removed by design.

COMMERCIAL IN CONFIDENCE

# Contents

Contents	2

1. Executive Summary	3

Investment summary	3

Why this route	3

2. Approach & Platform Stack	4

3. The Two Origination Flows	4

4. Solution Components	6

4.1  Umbraco CMS marketing site	6

4.2  Blazor staff back-office	6

4.3  PropFlo Wallet (.NET MAUI Blazor Hybrid)	6

4.4  Power Platform workflow	6

4.5  AI document extraction (Claude on Azure Linux)	6

4.6  Treasury, payout & reconciliation	6

5. Delivery & Timeline	7

6. Licensing & Running Costs	7

6.1  Microsoft licences — 10 users	7

6.2  Azure & other running costs	7

6.3  Total recurring picture	8

7. Monthly Maintenance & Support	9

Included in the retainer	9

Retainer terms	9

8. Risks & Honest Limits	9

9. Detailed Cost Breakdown	11

9.1  Phase 1 — Foundation, Website, Admin & Minimal Agent App	11

9.2  Phase 2 — Workflow & Treasury (Power Platform)	11

9.3  Phase 3 — AI Document Extraction (Claude on Linux)	12

9.x  Grand Total (build only)	12

10. Comparison, Assumptions & Terms	12

10.1  This build vs the full custom (agentic) build	13

10.2  Included	13

10.3  Excluded (paid separately / to vendors)	13

10.4  Key assumptions	13

10.5  Commercial terms	13

# 1. Executive Summary

This proposal sets out a build of the PropFlo bridging-finance platform on a pure Microsoft stack: Blazor for the staff back-office, Umbraco CMS for the public marketing site, a .NET MAUI Blazor Hybrid mobile app that reuses the Blazor components, Power Apps and Power Automate as the workflow engine, and Azure underneath — Azure SQL for the ledger, Entra ID for identity, and Claude (Anthropic) running on Azure Linux for document extraction.

It supports both origination flows — seller-side (attorney-originated) and agent-commission (agency/agent-originated) — with a single AI document-extraction step and a human reviewing and approving every advance. Delivery is split into three separately approvable phases — (1) foundation, website, admin and a minimal agent app; (2) workflow and treasury; (3) AI extraction — each costed below. It replaces the previously proposed Retool low-code route.

## Investment summary

| Item | Amount (excl. VAT) |
| --- | --- |
| Phase 1 — Foundation, Website, Admin & Minimal Agent App (496 hrs) | R421 600 |
| Phase 2 — Workflow & Treasury (Power Platform) (200 hrs) | R170 000 |
| Phase 3 — AI Document Extraction (Claude on Linux) (140 hrs) | R119 000 |
| Build total (excl. VAT) | R710 600 |
| VAT (15%) | R106 590 |
| Build total (incl. VAT) | R817 190 |
| PLUS Microsoft licences — 10 users (per year) | R93 240 |
| PLUS Azure hosting & AI usage (per year, indicative) | R51 600–R150 000 |
| PLUS monthly maintenance retainer (Section 7) | R17 000/mo |

The build total is a one-off. Licences, Azure consumption and the maintenance retainer are recurring; Section 6 and Section 7 break them down in full.

## Why this route

- Owned code where it matters: the Blazor admin, .NET API, MAUI app and Umbraco site belong to PropFlo — no vendor can reprice them.

- No per-agent fees at any volume: agents use PropFlo’s own web and mobile apps; only the 10 internal staff carry licences.

- Component reuse: the MAUI app is a hybrid shell around the same Blazor components as the web — one UI codebase, two channels.

- One ecosystem: identity, email, workflow and hosting under the Microsoft tenant; the Claude extraction service runs on Azure Linux alongside it.

# 2. Approach & Platform Stack

The platform combines custom .NET development (where ownership and control matter) with the licensed Power Platform (where configured workflow is faster and cheaper than code).

| Layer | Technology | Role — and who owns it |
| --- | --- | --- |
| Marketing website | Umbraco CMS (.NET) | Public site, calculator, lead capture — owned code |
| Staff back-office | Blazor (ASP.NET Core) | Admin, review & approval screens — owned code |
| Mobile Wallet | .NET MAUI Blazor Hybrid | Agent app reusing the Blazor components — owned code |
| Workflow | Power Apps + Power Automate | Intake, routing, chase, approvals — licensed platform |
| Data / ledger | Azure SQL | Advances, agents, parties, documents — owned data |
| Identity | Entra ID + Entra External ID | Staff + agent sign-in (one login web & app) |
| Document AI | Claude (Anthropic) on Azure Linux | Field extraction, human-reviewed — usage-billed |
| Hosting | Azure App Service | Web, API and CMS hosting — consumption-billed |

The dividing line is deliberate. Screens, data and the mobile app are custom and owned — they carry PropFlo’s money logic and must never be hostage to a vendor’s pricing. The workflow glue — mailbox monitoring, document routing, missing-document chasing, approvals and notifications — is configured in Power Automate and Power Apps, where a licensed platform genuinely is faster to build and cheaper to run than bespoke code. The Blazor components are written once and reused inside the MAUI hybrid shell, so the web portal and the mobile app share one UI codebase. The one deliberate exception to “pure Microsoft” is the extraction model itself: Claude, chosen for its document-understanding strength, runs in a container on Azure Linux with keys in Azure Key Vault — the infrastructure stays Azure.

# 3. The Two Origination Flows

Both flows are supported from day one. They enter through different channels and use different documents, then share the same ledger, review screens and payout process.

| Aspect | Seller-side | Agent-commission |
| --- | --- | --- |
| Originated by | Conveyancing / transferring attorney | Agency or agent |
| Advance against | Seller’s net sale proceeds | Pending commission earned |
| Entry channel | Seller-side intake mailbox | PropFlo app (deal list + uploads) / web portal |
| Key documents | OTP / Deed of Sale, seller FICA, attorney undertaking | Agency FFC, agent mandate, sale agreement, FICA |
| Workflow | Power Automate routes to matter; chase for gaps | Same engine, commission-specific checklist |

# 4. Solution Components

## 4.1  Umbraco CMS marketing site

A full Umbraco CMS marketing site — templated, responsive, with the savings calculator and lead-capture forms. Captured leads route into the platform via the API and Power Automate, triggering sales follow-up. Umbraco is open-source: no licence fee.

## 4.2  Blazor staff back-office

The admin portal is a Blazor (ASP.NET Core) application: advance lists and detail views, the workflow states (Applied → Review → Approved → Disbursed → Settled), role-based access, maker/checker approval gates, and the review screen where extracted document fields sit beside the source PDF for approve/edit.

## 4.3  PropFlo Wallet (.NET MAUI Blazor Hybrid)

The first release of the agent app is deliberately minimal: a list of the user’s deals and the ability to upload documents — in particular the attorney undertaking. It is a .NET MAUI hybrid hosting the same Blazor components as the web, so later Wallet features (balances, drawdown initiation, push notifications) extend the same codebase rather than a second app. Agents and attorneys sign in with Entra External ID; one identity covers web and app.

## 4.4  Power Platform workflow

Power Automate monitors the intake mailboxes for both flows, routes documents to the correct matter, runs the missing-document chase (reminders to agents and attorneys), and drives approvals with Teams/Outlook notifications. Power Apps provides quick internal utility forms where a configured screen beats custom code.

## 4.5  AI document extraction (Claude on Azure Linux)

Phase 3 adds a single extraction step powered by Claude (Anthropic), running as a service in a container on Azure Linux. Prompts and output schemas are designed per document type — OTP, FICA, FFC, mandates, undertakings — and every extraction is reviewed by the fund manager in the Blazor review screen before any decision. Extraction is a convenience, not an authority; manual keying remains the fallback.

## 4.6  Treasury, payout & reconciliation

The platform generates payout instructions and updates the ledger; the actual EFT remains a manual maker/checker process in the bank’s corporate portal. Daily bank-statement reconciliation marks advances settled per flow.

# 5. Delivery & Timeline

Delivery is three phases. Phase 1 ends with a usable system operated manually; Phase 2 automates the workflow; Phase 3 adds AI extraction.

| Phase | Indicative duration |
| --- | --- |
| Phase 1 — Foundation, website, admin & minimal agent app | 10–12 weeks |
| Phase 2 — Workflow & treasury (Power Platform) | 4–5 weeks |
| Phase 3 — AI document extraction (Claude) | 3–4 weeks |

Indicative elapsed timeline: approximately 4–6 months to full go-live with 1–2 developers. Phase 1 alone delivers a usable system (manual workflow) in roughly three months; Phases 2 and 3 are separately approvable and can be committed once Phase 1 has landed.

# 6. Licensing & Running Costs

Recurring costs come in three parts: Microsoft licences for the 10 internal staff, Azure consumption for hosting and AI usage, and the maintenance retainer (Section 7). Licence prices below are Microsoft’s published July 2026 rates, converted at an indicative R18.5/USD; the Rand amounts Microsoft actually bills in South Africa may differ slightly and should be confirmed with your CSP.

## 6.1  Microsoft licences — 10 users

| Licence | Per user / month | 10 users / month | Per year |
| --- | --- | --- | --- |
| Microsoft 365 Business Premium | USD 22 ≈ R407 | R4 070 | R48 840 |
| Power Apps Premium (full licence) | USD 20 ≈ R370 | R3 700 | R44 400 |
| Total Microsoft licences — 10 users |  | R7 770 | R93 240 |

What the licences cover. Microsoft 365 Business Premium (USD 22/user/month, unchanged in Microsoft’s July 2026 price increases) gives staff email, Office, Teams, device management and security. Power Apps Premium (USD 20/user/month) licenses each staff member for unlimited Power Apps and the premium connectors and Dataverse the workflow uses — the per-app plan was retired in January 2026, so Premium is the correct SKU. Flows that run inside the app context are covered by these licences; any standalone premium flows identified during architecture may need Power Automate licensing, confirmed at the start of Phase 1.

## 6.2  Azure & other running costs

| Item |  | Basis | Est. monthly (ZAR) |
| --- | --- | --- | --- |
| Azure hosting |  | App Service, Azure SQL, storage, Linux extraction host | R4 000–10 000 |
| Claude API usage (extraction) |  | Per-document usage, scales with volume | R300–2 500 |
| Entra External ID (agent sign-in) |  | Free tier ≤ 50,000 monthly active users | R0 |
| Umbraco CMS licence |  | Open source, self-hosted on Azure | R0 |
| Apple Developer + Google Play |  | ≈R1,850/yr + R475 once-off | ≈R160 |
| No per-agent licence fees — the cost this stack removes. Agents never touch a licensed seat. They use PropFlo’s own MAUI app and Blazor web portal, signing in through Entra External ID — free for the first 50,000 monthly active users. Whether PropFlo has 50 agents or 3,000, the licence bill stays the same: 10 staff seats. Under the Retool route this proposal replaces, 1,000 active agents would have cost roughly R94,000 per month in external-user fees alone. Here that number is zero. |  |  |  |

## 6.3  Total recurring picture

| Recurring item | Monthly (ZAR) |
| --- | --- |
| Microsoft licences (10 users) | R7 770 |
| Azure hosting + Claude API usage | R4 300–12 500 |
| Maintenance retainer (Section 7) | R17 000 |
| Indicative total recurring | R29 070–37 270/mo |
| Per-agent licence fee — at any number of agents | R0 |

# 7. Monthly Maintenance & Support

A production system that pays out money needs standing care, not ad-hoc fixes. This proposal includes a monthly maintenance retainer from go-live:

| Retainer | Amount |
| --- | --- |
| Monthly maintenance & support — 20 hours @ R500 | R17 000/mo excl. VAT |
| Annualised | R204 000/yr excl. VAT |

## Included in the retainer

- Azure platform care: patching, monitoring, backups verification, cost review.

- Umbraco CMS updates and security patches; content-editor support.

- MAUI app upkeep: iOS/Android OS-release compatibility and store re-submissions — mobile apps require periodic updates simply to keep working.

- Power Platform upkeep: flow failures, connector changes, licence/API-limit monitoring.

- Claude extraction upkeep: prompt and schema updates as documents evolve; model-version pinning and regression checks.

- Minor changes and fixes within the monthly hours; priority response on production incidents.

## Retainer terms

- 20 hours per month at R850/hour = R17,000/month excl. VAT (R204,000/year), from go-live.

- Unused hours do not accumulate; work beyond the retainer is quoted or billed at R850/hour by agreement.

- Either party may adjust or cancel on three months’ written notice.

# 8. Risks & Honest Limits

This route removes the per-agent cost risk, but it is not risk-free. The material points, stated plainly:

Document processing is still one AI step plus a human — not the agentic engine. Claude extracts fields; the fund manager verifies every advance. There are no deterministic gates, no multi-LLM fallback (a single AI provider, with manual keying as the fallback), and no versioned learning loop — those belong to the full custom build (~R4.6m). The human reviewer remains the main control, which is appropriate at moderate volume but is a scaling constraint, not a solved problem.

- Power Platform licensing grows with staff, not agents: each additional staff member who uses the workflow needs an M365 + Power Apps Premium seat (~R777/month at current rates).

- Power Platform has service limits — daily API request allowances per user and Dataverse storage (R≈40/GB/month beyond pooled capacity). The design keeps the ledger in Azure SQL to minimise Dataverse exposure, but heavy flow volumes can require add-ons.

- Ecosystem concentration: identity, email, workflow, hosting and AI all sit with Microsoft. The Blazor/MAUI/Umbraco code is portable; the Power Automate flows are the locked-in layer and would need rebuilding if PropFlo ever left the ecosystem.

- Custom development needs .NET skill and discipline — slower to change than drag-and-drop low-code, though far more controllable.

- Claude extraction is usage-billed per document and passed through at cost; Anthropic’s API pricing sits outside the Microsoft licence stack and is subject to its own changes.

- Licence prices are Microsoft’s to change. Business Premium survived the July 2026 increases unchanged, but future rises land directly on the monthly bill.

# 9. Detailed Cost Breakdown

All build work is charged at R850 per hour (excl. VAT). Each phase is a separately approvable, separately invoiced deliverable — Phases 2 and 3 can be committed once Phase 1 has delivered. The estimate is quoted lean — no separate project-management or contingency lines — so it is tight against the hours; material scope changes are quoted separately. Licences, Azure and maintenance (Sections 6–7) are recurring and additional.

## 9.1  Phase 1 — Foundation, Website, Admin & Minimal Agent App

| Work item | Hours | Cost |
| --- | --- | --- |
| Requirements & process mapping | 12 | R10 200 |
| Solution architecture (Blazor / MAUI / Power Platform / Azure SQL) | 16 | R13 600 |
| Azure environment: App Service, SQL, storage, Key Vault, CI/CD | 16 | R13 600 |
| M365 tenant, Entra ID configuration & security baseline | 8 | R6 800 |
| Azure SQL schema: deals, agents, agencies, attorneys, parties, documents | 28 | R23 800 |
| .NET API layer shared by Blazor, MAUI and Power Platform | 36 | R30 600 |
| Identity: Entra ID (staff) + Entra External ID (agents/attorneys; one login web + app) | 28 | R23 800 |
| Umbraco CMS: install, configuration & base scaffolding | 24 | R20 400 |
| Umbraco CMS: marketing site design, templating & responsive build | 48 | R40 800 |
| Savings calculator web-app | 24 | R20 400 |
| Lead capture forms & routing into the platform | 24 | R20 400 |
| Meta campaign landing pages & tracking pixels | 16 | R13 600 |
| Blazor admin: agents, agencies & attorneys (onboarding, FICA/FFC records) | 40 | R34 000 |
| Blazor admin: deal list & detail with workflow states (manual operation) | 36 | R30 600 |
| Blazor admin: review & maker/checker approval screens | 28 | R23 800 |
| Blazor admin: document repository & viewer | 16 | R13 600 |
| Blazor admin: basic reporting & exports | 12 | R10 200 |
| Agent app (.NET MAUI Blazor Hybrid): shell & component reuse | 20 | R17 000 |
| Agent app: list of deals | 12 | R10 200 |
| Agent app: upload undertaking & supporting documents | 16 | R13 600 |
| Agent app: store submission & signing (Apple / Google) | 12 | R10 200 |
| Phase 1 testing, training & release | 24 | R20 400 |
| Phase subtotal | 496 | R421 600 |

## 9.2  Phase 2 — Workflow & Treasury (Power Platform)

| Work item | Hours | Cost |
| --- | --- | --- |
| Workflow design: Applied → Review → Approved → Disbursed → Settled | 20 | R17 000 |
| Power Automate: intake mailbox monitoring & document routing (both flows) | 32 | R27 200 |
| Missing-document chase flows: reminders & notifications | 28 | R23 800 |
| Approval flows & Teams / Outlook notifications | 20 | R17 000 |
| Power Apps utility forms for internal operations | 12 | R10 200 |
| Payout instruction generation & ledger state updates | 20 | R17 000 |
| Maker/checker process around the bank portal (manual EFT) | 12 | R10 200 |
| Per-flow settlement tracking | 16 | R13 600 |
| Daily bank-statement reconciliation tooling | 20 | R17 000 |
| Phase 2 testing & release | 20 | R17 000 |
| Phase subtotal | 200 | R170 000 |

## 9.3  Phase 3 — AI Document Extraction (Claude on Linux)

| Work item | Hours | Cost |
| --- | --- | --- |
| Claude extraction service on Azure Linux (container, API integration, Key Vault) | 32 | R27 200 |
| Prompt & output-schema design per document type (OTP, FICA, FFC, mandate, undertaking) | 36 | R30 600 |
| Human review integration in Blazor (approve / edit) | 24 | R20 400 |
| Confidence thresholds & manual-keying fallback | 12 | R10 200 |
| Evaluation set & accuracy testing on sample documents | 20 | R17 000 |
| Phase 3 testing & release | 16 | R13 600 |
| Phase subtotal | 140 | R119 000 |

## 9.x  Grand Total (build only)

| Summary | Hours | Cost |
| --- | --- | --- |
| Phase 1 — Foundation, Website, Admin & Minimal Agent App | 496 | R421 600 |
| Phase 2 — Workflow & Treasury (Power Platform) | 200 | R170 000 |
| Phase 3 — AI Document Extraction (Claude on Linux) | 140 | R119 000 |
| Build subtotal | 836 | R710 600 |
| Build total (excl. VAT) |  | R710 600 |
| Build total (incl. 15% VAT) |  | R817 190 |

# 10. Comparison, Assumptions & Terms

## 10.1  This build vs the full custom (agentic) build

| Dimension | Microsoft stack (this proposal) | Umbraco custom (agentic) |
| --- | --- | --- |
| Build cost (ex VAT) | R710 600 | ~R4.01m |
| Time to go-live | 4–6 months | 9–12 months |
| Per-agent fee | None — at any volume | None — no per-seat |
| Staff licences | 10 × M365 + Power Apps ≈ R7 770/mo | M365 as needed |
| Workflow engine | Power Platform (licensed) | Custom orchestration (owned) |
| Document processing | Claude extraction + human review | Multi-agent + human sign-off |
| Deterministic gates | — | Hard, code-level |
| Multi-LLM fallback | — | Claude + ChatGPT + GLM |
| Mobile app | MAUI Blazor Hybrid (owned) | Native app (owned) |
| Ownership | Code owned; workflow licensed | Full code ownership |
| Best for | Fast, owned, cost-safe scaling | Long-term regulated autonomy |

The Retool low-code route previously proposed has been withdrawn at PropFlo’s direction and is not compared here.

## 10.2  Included

- All design, development, configuration, AI-model setup and testing in Sections 2–5 and 9.

- Store submissions, staff training, runbooks and a hypercare period at go-live.

## 10.3  Excluded (paid separately / to vendors)

- Microsoft licences, Azure consumption, Claude API usage, Apple/Google store fees (Section 6) — procured in PropFlo’s name.

- Meta ad spend and creative; legal, FICA, FSP/NCR licensing and regulatory advice.

- The agentic underwriting engine, deterministic gates, multi-LLM fallback and learning loop (full custom build).

## 10.4  Key assumptions

- Manual EFT with maker/checker remains the payout mechanism; no automated bank integration.

- AI extraction is decision-support with mandatory human verification on every advance.

- Licence pricing per Microsoft’s published July 2026 rates at an indicative R18.5/USD; ZA billing to be confirmed via CSP at the start of Phase 1.

- PropFlo provides timely access to stakeholders, branding, banking portals and sample documents for extraction tuning.

## 10.5  Commercial terms

- Rate R850/hour excl. VAT; VAT at 15% where applicable. Billed monthly in arrears against actual hours.

- Maintenance retainer R17,000/month excl. VAT from go-live (Section 7).

- Payment terms 30 days; 20% deposit on commencement of each phase. Proposal valid 30 days from the cover date.

- Change control: scope changes quoted and approved in writing first.

This stack gives PropFlo owned code on the surfaces that matter, a licensed workflow engine where configuration beats code, and — decisively — zero per-agent fees at any volume. Happy to walk through the architecture and the licence picture in detail.