## Slide 1
PropFlo Marketing Launch Programme
Project Management Pack — editable (CPM/PERT schedule, Gantt, milestones, RACI, risk)
Prepared by Interon · Commercial in confidence · Working draft · All costs ex VAT
Calculated by Critical Path Method. Stage A = 49 working days (~10 wks); programme ~159 calendar days (~5.2 months).

## Slide 2
Project Summary
• Two stages: Stage A (preparation) then Stage B (true 90-day live campaign). The 90-day clock starts at launch.
• Calculated Stage A: 49 working days (~10 weeks; ~15 weeks pessimistic).
• Critical path: compliance → landing-page copy & build → pages approval → tracking test → campaign build → testing → launch.
• Budget ex VAT: R233,500–R283,500 across overlap scenarios; R32,000/month management after Day 90. Platform build separate.
• Unresolved commercial items (B1–B7) are flagged, not resolved.

## Slide 3
Critical Path (Stage A) — dark boxes = milestone gates
◆ A0
Project authorisation
A1 (2d)
Kick-off & roles
A2 (1d)
Stakeholder confirm
A5 (6d)
Discovery & compliance
A6 (3d)
Compliance questions
A7 (6d)
Approved claims
A9 (3d)
Required disclaimers
◆ M1
Compliance & claims approved
A18 (6d)
Landing page copy
A19 (11d)
Landing page build
A21 (2d)
Landing page QA
◆ M3
Landing pages approved
A26 (2d)
Tracking end-to-end test
◆ M4
Tracking approved
A33 (3d)
Campaign build
◆ M6
Campaigns approved
A37 (3d)
Pre-launch testing
A38 (1d)
Launch checklist
◆ M7
CONTROLLED LAUNCH
→ then Stage B (from launch): Day 0 → 7 → 14 → 30 → 45 → 60 → 75 → 90 scale decision (true 90 live days).

## Slide 4
Milestone Timeline (even spacing, not to day-scale)
Authorisation
D0
Kick-off
D3
Compliance confirmed
D17
Strategy approved
D25
Claims approved
D29
Lead handling ready
D36
Landing pages approved
D56
Tracking approved
D59
Campaigns approved
D63
CONTROLLED LAUNCH
D69
Day 7 review
D76
Day 14 review
D83
Day 30 review
D99
Day 45 checkpoint
D114
Day 60 review
D129
Day 75 checkpoint
D144
Day 90 decision
D159

## Slide 5
Programme Gantt — Overview (calendar days from authorisation)
D0
D14
D28
D42
D56
D70
D84
D98
D112
D126
D140
D154
Stage A prep
49 working days (~10 wks)
Stage B live
90 live days
LAUNCH D69
Milestones
M2
M1
M3
M6
D30
D60
D90
Detailed per-activity Gantt (Stage A & B) is in the SVG folder, the .drawio file, and the Excel/MS Project CSV.

## Slide 6
RACI Matrix — R Responsible · A Accountable · C Consulted · I Informed
Activity | Sponsor | Compl/Legal | Sales | Interon PL | Strategy | Paid Media | Content/SEO | Design | Dev/Tech
Proposal & budget approval | A | C | I | R | C | I | I | I | I
Compliance & claims | A | R | C | C | C | I | C | I | I
Strategy & research | C | C | C | A | R | C | C | I | I
Website & landing pages | A | C | C | R | C | C | C | R | R
Tracking & measurement | I | I | C | A | C | R | I | I | R
Paid search | I | C | I | A | C | R | I | I | I
Meta retargeting | I | C | I | A | C | R | C | C | I
SEO & content | I | C | I | A | C | I | R | I | I
Partner & LinkedIn | C | C | C | A | R | I | C | C | I
Email & WhatsApp | I | C | R | A | C | I | C | I | I
CRM & lead mgmt | C | I | R | A | C | I | I | I | C
Reporting & optimisation | C | I | C | A | C | R | C | I | I
Project management | A | I | I | R | C | C | C | I | I

## Slide 7
Risk Register (severity: red High · amber Medium · green Low)
ID | Risk | Probability | Impact | Severity
R1 | Compliance approval delay | High | High | High
R2 | Claims/ads rejected by platform | Med | High | High
R3 | Poor landing page conversion | Med | High | High
R4 | Slow lead response | Med | High | High
R5 | Poor lead quality | Med | High | High
R6 | Insufficient sales feedback | Med | High | High
R7 | Tracking gaps | Med | High | High
R8 | Budget pressure | Med | Med | Medium
R9 | Platform restrictions | Med | Med | Medium
R10 | Scope overlap / double charge | High | Med | High
R11 | Delayed client approvals | Med | High | High
R12 | CRM / lead process failure | Med | High | High
R13 | Build/marketing timeline mismatch | High | Med | High
R14 | Weak or unclear offer | Med | High | High
Full mitigations, owners and triggers are in RISK-REGISTER.html and MASTER-PROJECT-PLAN.md Section 13.